## Worksheet
Event Planning - Project Plan (Analysis View)
Phase | Task Name | Owner | Start Date | End Date | Status | Budget (USD) | Milestones & Dependencies
Phase 1: Planning & Requirements Gathering
Planning | Define Event Objectives & Scope | Project Manager | 2024-04-01 | 2024-04-05 | In Progress | $1,500 | Budget Approved, Stakeholder Sign-off Required
Planning | Identify Target Audience & Goals | Marketing Lead | 2024-04-06 | 2024-04-10 | Pending | $850 | Input from Survey Data (Due: 2024-04-15)
Phase 2: Logistics & Vendor Coordination
Logistics | Select Event Venue | Facilities Manager | 2024-04-11 | 2024-04-18 | Pending | $5,000 | Venue Contracts Due: 2024-04-25
Logistics | Book Catering & Audiovisual Services | Operations Lead | 2024-04-15 | 2024-04-23 | Pending | $8,750 | Venue Confirmation Required First
Phase 3: Marketing & Communications Strategy
Marketing | Design Event Branding & Materials | Graphic Designer | 2024-04-16 | 2024-04-28 | Pending | $3,500 | Approval from Marketing Lead (Due: 2024-04-30)
Marketing | Launch Email & Social Media Campaigns | Digital Marketing Specialist | 2024-05-01 | 2024-05-15 | Pending | $6,800 | Branding Approved; Registration Portal Ready (Due: 2024-04-31)
Phase 4: Final Preparations & Execution
Prep | Confirm Attendee List & Registration | Event Coordinator | 2024-05-16 | 2024-05-25 | Pending | $1,200 | All Marketing Materials Live; System Testing Complete (Due: 2024-05-31)
Prep | Finalize Event Schedule & Run-through | Project Manager | 2024-05-26 | 2024-05-31 | Pending | $1,800 | Final Team Meeting: 2024-05-31; Final Sign-off Required
Total Budget: | [5 empty] | $29,400