## Event Planning Project Plan
Event Planning Project Plan
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
T001 | Define event goals and objectives | Jane Smith | 2024-04-05 | 2024-04-10 | Completed
T002 | Select event date and venue | Jane Smith | 2024-04-11 | 2024-04-15 | In Progress
T003 | Create guest list and send invitations | Mark Johnson | 2024-04-16 | 2024-04-25 | Pending
T004 | Arrange catering and refreshments | Sarah Lee | 2024-04-18 | 2024-04-30 | In Progress
T005 | Book entertainment and speakers | David Brown | 2024-04-19 | 2024-04-28 | In Progress
T006 | Design and print event materials (banners, signage) | Lisa Wong | 2024-04-17 | 2024-05-01 | Pending
T007 | Finalize event schedule and timeline | Jane Smith | 2024-05-01 | 2024-05-03 | Pending
T008 | Conduct final walkthrough and setup rehearsal | All Team Members | 2024-05-15 | 2024-05-16 | Pending
T009 | Event day coordination and execution | Jane Smith, Mark Johnson, Sarah Lee, David Brown, Lisa Wong | 2024-05-17 | 2024-05-17 | Pending
T010 | Post-event evaluation and feedback collection | Jane Smith, All Team Members | 2024-05-18 | 2024-05-25 | Pending
*Note: This is a basic project plan template for event planning. Update statuses and dates as needed.