## Worksheet
Task ID | Task Name | Start Date | End Date | Assigned To | Status | Priority
EP001 | Define Event Objectives | 2023-10-01 | 2023-10-05 | Jane Doe | Completed | High
EP002 | Select Venue & Date | 2023-10-06 | 2023-10-15 | John Smith | In Progress | High
EP003 | Develop Event Budget | 2023-10-16 | 2023-10-25 | Alice Brown | To Do | Medium
EP004 | Invite Attendees | 2023-10-26 | 2023-11-15 | Maria Garcia | To Do | High
EP005 | Arrange Catering & Logistics | 2023-11-01 | 2023-11-30 | Robert Wilson | To Do | High
EP006 | Create Event Schedule & Agenda | 2023-11-20 | 2023-11-30 | Sophia Martinez | To Do | Medium
EP007 | Coordinate Marketing Campaign | 2023-11-15 | 2023-11-30 | Liam Anderson | To Do | Medium
EP008 | Finalize Event Setup & Decorations | 2023-11-25 | 2023-11-30 | Ella Taylor | To Do | High
EP009 | Conduct Event Walkthrough & Rehearsal | 2023-11-30 | 2023-11-30 | Jane Doe | To Do | High
EP010 | Post-Event Debrief & Report | 2023-12-05 | 2023-12-15 | All Team Members | To Do | Low
Total Tasks: | [5 empty] | 10