## Worksheet
Event Planning Project Plan - Client View
Task ID | Task Name | Responsible Party | Start Date | End Date | Status
EVT-001 | Define Event Objectives & Scope | Project Manager | 2024-04-01 | 2024-04-05 | In Progress
EVT-002 | Finalize Budget Approval | Finance Team | 2024-04-06 | 2024-04-10 | Pending
EVT-003 | Select Venue & Confirm Booking | Logistics Coordinator | 2024-04-11 | 2024-04-18 | Not Started
EVT-004 | Arrange Catering & Venue Setup | Catering Manager | 2024-04-15 | 2024-04-25 | Not Started
EVT-005 | Invite Attendees & Manage RSVPs | Marketing Team | 2024-04-18 | 2024-05-10 | Not Started
EVT-006 | Finalize Program & Speaker Confirmations | Event Coordinator | 2024-05-01 | 2024-05-15 | Not Started
EVT-007 | Event Day Setup & Runthrough | All Teams | 2024-05-25 | 2024-05-26 | Not Started
EVT-008 | Post-Event Feedback Collection & Reporting | Project Manager | 2024-05-27 | 2024-06-03 | Not Started
Project Plan Status as of April 1, 2024 - Client View