## Worksheet
Task | Start Date | End Date | Responsible | Status
Define Event Scope | 2024-05-01 | 2024-05-03 | Jane Doe | In Progress
Secure Venue | 2024-05-04 | 2024-05-10 | John Smith | Pending
Create Guest List | 2024-05-11 | 2024-05-13 | Alice Brown | Not Started
Send Invitations | 2024-05-14 | 2024-05-17 | Alice Brown | Not Started
Arrange Catering | 2024-05-18 | 2024-05-20 | Mike Johnson | Pending
Confirm Speakers | 2024-05-19 | 2024-05-21 | Jane Doe | Pending
Set Up Audiovisual Equipment | 2024-05-25 | 2024-05-27 | Tom Wilson | Not Started
Cleanup & Final Review | 2024-05-30 | 2024-05-31 | All Team Members | Not Started
Total Tasks |  |  |  | 8