## Worksheet
Daily Project Plan - Event Planning
Task ID | Task Description | Assigned To | Status | Due Date | Daily Progress (%)
Monday, April 15, 2024
TP-001 | Finalize event theme and color scheme | Jane Doe | In Progress | 2024-04-15 | 75%
TP-002 | Schedule venue visit and secure booking | John Smith | Not Started | 2024-04-16 | 15%
Tuesday, April 16, 2024
TP-003 | Confirm catering menu and vendor contract | Lisa Wong | Not Started | 2024-04-17 | 5%
Wednesday, April 17, 2024
TP-004 | Design and distribute digital invitations | Mark Lee | In Progress | 2024-04-18 | 60%
Thursday, April 18, 2024
TP-005 | Finalize guest list and send RSVP reminders | Sarah Johnson | In Progress | 2024-04-19
Friday, April 19, 2024
TP-006 | Coordinate audiovisual setup and technical rehearsal | Robert Brown
Generated on: April 14, 2024 ¦ Project ID: EVT-2024-DAILY-PLAN