## Event Planning - Project Plan
Event Planning - Project Plan (Data Version)
Task ID | Task Description | Responsible Team | Start Date | End Date | Status | % Complete
EVT-001 | Define Event Objectives and Scope | Event Planning Team | 2023-10-01 | 2023-10-05 | In Progress | 75%
EVT-002 | Secure Venue and Permits | Logistics Team | 2023-10-06 | 2023-10-15 | To Do | 0%
EVT-003 | Develop Marketing and Promotion Plan | Marketing Team | 2023-10-10 | 2023-10-25 | In Progress | 60%
EVT-004 | Finalize Guest List and RSVP Tracking | Operations Team | 2023-10-18 | 2023-11-05 | To Do | 0%
EVT-005 | Coordinate Catering and Onsite Services | Catering Team | 2023-10-15 | 2023-11-10 | In Progress | 55%
EVT-006 | Develop Event Schedule and Agenda | Event Coordination Team | 2023-10-20 | 2023-11-08 | To Do | 0%
EVT-007 | Conduct Final Event Walkthrough and Rehearsal | Event Management Team | 2023-11-15 | 2023-11-20 | To Do | 0%
Total Tasks: | [5 empty] | 7
Note:This project plan is updated weekly. All dates are subject to change based on resource availability and external factors.