## Worksheet
Event Planning - Project Plan (Detailed)
Task ID | Task Name | Responsible Party | Start Date | End Date | Status | % Complete | Budget (USD)
Phase 1: Planning & Setup (Weeks 1-2)
TP-001 | Define Event Objectives & Scope | Project Manager | 2023-10-02 | 2023-10-06 | In Progress | 85% | $1,500
TP-002 | Establish Project Team & Roles | Project Manager | 2023-10-03 | 2023-10-07 | In Progress | 95% | $500
TP-003 | Develop Event Budget Plan | Finance Lead | 2023-10-04 | 2023-10-11 | Pending | 5% | $3,500
Phase 2: Venue & Logistics (Weeks 3-5)
TP-004 | Identify and Shortlist Venues | Venue Coordinator | 2023-10-15 | 2023-10-26 | Pending | 5% | $800
TP-005 | Negotiate Venue Contract & Book Space | Venue Coordinator | 2023-10-27 | 2023-11-03 | Pending | 5% | $8,500
TP-006 | Arrange Catering & Dietary Options | Catering Manager | 2023-11-04 | 2023-11-17 | Pending | 5% | $6,000
Phase 3: Marketing & Communications (Weeks 4-7)
TP-007 | Design Event Branding & Visual Identity | Marketing Designer | 2023-11-04 | 2023-11-16 | Pending | 5% | $3,000
TP-008 | Create Event Website & Registration Page | Web Developer | 2023-11-17 | 2023-12-07 | Pending | 5% | $4,500
Phase 4: Speaker & Program Management (Weeks 6-9)
TP-009 | Identify & Invite Keynote Speakers | Program Director | 2023-11-25 | 2023-12-14 | Pending | 5% | $9,000
Phase 5: Final Preparations (Weeks 10-12)
TP-013 | Finalize Event Schedule & Timetable | Project Manager | 2024-01-08 | 2024-01-15 | Pending | 5% | $3,500
M-01 | Project Kickoff Complete | Project Manager | 2023-10-16 | 2023-10-17 | In Progress | 95%
Total Project Budget: | [5 empty] | $45,800