## Worksheet
Event Planning Project Plan (Extended Template)
Task ID | Task Name | Responsible Team/Person | Timeline & Milestones |  |  |  | Status | Dependencies
|  |  | Start Date | Due Date | Duration (Days) | Milestone
EVT-001 | Define Event Objective & Scope | Project Manager, Marketing Lead | 2024-01-15 | 2024-01-25 | 10 | Concept Approved | In Progress | -
Venue & Logistics Planning (Phase 1)
EVT-002 | Identify & Shortlist Venues | Logistics Team, Venue Coordinator | 2024-01-26 | 2024-01-31 | 5 | Venue Options Finalized | In Progress | EVT-001, EVT-003
EVT-003 | Secure Venue Contract & Deposit Payment | Finance Officer, Legal Advisor | 2024-02-01 | 2024-02-15 | 14 | Venue Confirmed & Signed | Pending Review | EVT-002, EVT-007
Vendor Management (Phase 2)
EVT-004 | Procure Catering Services | Catering Coordinator, Procurement Officer | 2024-01-30 | 2024-02-15 | 16 | Catering Agreement Signed | In Progress | EVT-003, EVT-019, EVT-024
EVT-005 | Book Audio/Visual Equipment & Tech Team | IT Lead, AV Specialist | 2024-01-30 | 2024-02-18 | 19 | AV Setup Finalized | In Progress | EVT-037, EVT-035, EVT-036
Guest & Marketing (Phase 3)
EVT-012 | Design Event Branding & Promotional Materials | Graphic Designer, Marketing Team | 2024-01-28 | 2024-03-15 | 47 | Marketing Collateral Complete | In Progress | EVT-013, EVT-017, EVT-029
EVT-015 | Launch Event Website & Registration Portal | Web Developer, Marketing Coordinator | 2024-03-16 | 2024-03-31 | 15 | Registration Live & Functional | Pending Review | EVT-012, EVT-038, EVT-046
Final Preparations & Execution (Phase 4)
EVT-031 | Conduct Final Site Walkthrough & Setup Check | Event Manager, Facilities Lead | 2024-04-15 | 2024-04-17 | 3 | Venue Ready for Event Day | Pending Review | EVT-035, EVT-036, EVT-037, EVT-042
Post-Event Activities (Phase 5)
EVT-049 | Conduct Post-Event Review Meeting & Report | Project Manager, All Leads | 2024-05-18 | 2024-05-19 | 1 | All Feedback Collected & Documented | Pending Review | EVT-048, EVT-053, EVT-061, EVT-064
Total Tasks: |  |  | 27 | 89 (avg. duration) | 153 Days (total project timeline) | Overall Status: In Progress
Note:This table is a dynamic project plan template for event planning. All dates and statuses are illustrative and should be updated regularly during execution.