## Worksheet
Freelancer Event Planning Project Plan
Task ID | Task Name | Timeline |  |  | Responsible | Status | Notes
|  | Start Date | End Date | Duration (Days)
001 | Define Event Scope & Objectives | 2024-03-05 | 2024-03-15 | 11 | Jane Doe - Planner Lead | In Progress | Clarify client expectations and event goals.
002 | Select Venue & Confirm Availability | 2024-03-16 | 2024-03-18 | 3 | Jane Doe - Planner Lead | Pending | Negotiate contract terms with preferred vendors.
003 | Develop Budget Proposal | 2024-03-19 | 2024-03-21 | 3 | Alex Smith - Finance Coordinator | Pending | Submit to client for approval.
004 | Hire Catering & Entertainment Teams | 2024-03-22 | 2024-03-25 | 4 | Jane Doe - Planner Lead | Pending | Finalize contracts and timelines.
005 | Create Guest Invitations & RSVP System | 2024-03-26 | 2024-03-31 | 6 | Lisa Chen - Marketing Assistant | Pending | Email and social media campaign.
006 | Design Event Decor & Layout Plan | 2024-04-01 | 2024-04-15 | 15 | Maria Gonzalez - Creative Designer | Pending | Share mockups with client for feedback.
007 | Coordinate Logistics & Vendor Deliveries | 2024-04-16 | 2024-05-15 | 31 | Jane Doe - Planner Lead | Pending | Track all deliveries and on-site setup.
008 | Conduct Full Event Rehearsal | 2024-05-16 | 2024-05-17 | 2 | Jane Doe - Planner Lead & Team Leads | Pending | Final checks and team briefing.
009 | Event Day Execution & On-Site Management | 2024-05-18 | 2024-05-18 | 1 | Jane Doe - Planner Lead & Team Members | Pending | Ensure flawless event delivery.
010 | Post-Event Evaluation & Feedback Collection | 2024-05-19 | 2024-05-23 | 5 | Alex Smith - Finance Coordinator & Lisa Chen - Marketing Assistant | Pending | Gather client and attendee feedback.
Total Tasks |  | 10 Tasks