## Worksheet
Event Planning Project Plan - Home Use
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Notes/Comments
EVT-001 | Define event purpose and theme | Jane Doe | 2023-10-05 | 2023-10-07 | Completed | Theme chosen: Garden Party 2024
EVT-002 | Select venue and confirm availability | John Smith | 2023-10-08 | 2023-10-15 | In Progress | Venue booked at Oak Hill Estate
EVT-003 | Develop guest list and send invitations | Jane Doe | 2023-10-16 | 2023-10-25 | Pending | Invitations to be sent via email and physical mail
EVT-004 | Arrange catering and menu selection | Mike Johnson | 2023-10-18 | 2023-10-27 | Pending | Tasting session scheduled for 10/24
EVT-005 | Hire entertainment and set schedule | Sarah Lee | 2023-10-20 | 2023-11-05 | Pending | Bands and DJ under negotiation
EVT-006 | Order decorations and supplies | Emily Chen | 2023-10-22 | 2023-11-10 | Pending | Dress-up themes: Vintage Garden & Floral Fantasy
EVT-007 | Finalize event timeline and run-through rehearsal | Jane Doe | 2023-11-15 | 2023-11-20 | Pending | Full rehearsal scheduled for 11/18 at venue
EVT-008 | Coordinate logistics and on-site setup team | John Smith | 2023-11-25 | 2023-11-30 | Pending | All vendors to confirm arrival times and setup procedures
Event Day: December 1, 2023 - Final Check & Execution