## Worksheet
Event Planning Project Plan
Task ID | Task Description | Owner | Start Date | Due Date | Status | % Complete
Phase 1: Planning & Strategy (Jan 01 - Jan 15)
EVT-001 | Define Event Objectives and KPIs | Jane Smith | 2024-01-01 | 2024-01-05 | Completed | 100%
EVT-002 | Develop Target Audience Profile | Mark Johnson | 2024-01-03 | 2024-01-10 | In Progress | 75%
EVT-003 | Set Budget Approval Framework | Lisa Wong | 2024-01-06 | 2024-01-15 | In Progress | 55%
Phase 2: Venue & Logistics (Jan 16 - Feb 05)
EVT-004 | Secure Primary Event Venue | David Kim | 2024-01-16 | 2024-01-31 | In Progress | 85%
EVT-005 | Finalize Catering & Beverage Contracts | Sophia Lee | 2024-01-18 | 2024-02-03 | Delayed | 65%
Phase 3: Marketing & Promotion (Feb 01 - Feb 28)
EVT-006 | Design Event Branding & Collateral | Emma Rodriguez | 2024-02-01 | 2024-02-15 | In Progress | 88%
EVT-007 | Launch Digital Marketing Campaign | Alex Turner | 2024-02-15 | 2024-02-28 | Completed | 100%
Phase 4: On-Site Execution (Mar 01 - Mar 31)
EVT-008 | Coordinate Staff & Volunteer Scheduling | Olivia Brown | 2024-03-01 | 2024-03-15 | In Progress | 67%
EVT-009 | Set Up Event Infrastructure & Tech Systems | Marcus Evans | 2024-03-16 | 2024-03-31 | Delayed | 58%
Phase 5: Post-Event Review (Apr 01 - Apr 15)
EVT-010 | Conduct Post-Mortem Analysis & Report | Jane Smith | 2024-04-01 | 2024-04-15 | Completed | 100%
Overall Project Progress: | [5 empty] | 76%
Project Summary
Event Name:Annual Global Innovation Summit 2024
Total Tasks:10 ¦Completed:5 ¦In Progress:3 ¦Delayed:2
⚠️ Critical Delay Alert: Venue Setup and Tech Infrastructure are behind schedule. Immediate action required.
Next Milestone Deadline: March 15, 2024