## Worksheet
Event Planning Project Plan - Manager View
Task ID | Task Description | Owner | Start Date | Due Date | Status | % Complete | Budget (USD)
EP-001 | Define Event Objectives & Scope | Project Manager | 2023-10-05 | 2023-10-12 | In Progress | 65% | $5,000
EP-002 | Select Event Venue & Confirm Booking | Logistics Coordinator | 2023-10-13 | 2023-10-19 | Pending | 5% | $45,000
EP-003 | Develop Event Marketing & Promotion Plan | Marketing Lead | 2023-10-14 | 2023-11-15 | Pending | 7% | $28,000
EP-004 | Finalize Speaker & Guest List | Event Coordinator | 2023-10-18 | 2023-11-05 | In Progress | 45% | $18,000
EP-005 | Develop Event Agenda & Schedule | Program Director | 2023-10-16 | 2023-11-18 | Pending | 4% | $7,500
EP-006 | Design & Print Event Materials | Design Team Lead | 2023-11-05 | 2023-11-30 | Pending | 2% | $9,800
EP-007 | Set Up Onsite Logistics & Staffing | Operations Manager | 2023-11-25 | 2023-12-15 | Pending | 0% | $48,750
EP-008 | Conduct Final Event Rehearsal | Event Director | 2023-12-14 | 2023-12-15 | Pending | 0% | $5,400
Total Budget: | [6 empty] | $171,450
Project Health:On Track ¦Overall Progress:26% ¦Status Update Date:October 5, 2023