## Worksheet
Task | Responsible Person | Start Date | End Date | Status | Milestone
January 2024
Define event objectives and target audience | Project Manager | 01/05/2024 | 01/10/2024 | In Progress | Yes
Secure venue booking and confirm availability | Venue Coordinator | 01/07/2024 | 01/15/2024 | Pending | Yes
Create initial budget proposal | Finance Lead | 01/03/2024 | 01/12/2024 | Completed | No
February 2024
Finalize vendor contracts (catering, AV, decor) | Procurement Officer | 02/01/2024 | 02/14/2024 | In Progress | Yes
Publish event invitations and registration portal open | Marketing Manager | 02/10/2024 | 02/18/2024 | Pending | Yes
Develop event agenda and speaker lineup | Event Coordinator | 02/05/2024 | 02/13/2024 | In Progress | No
March 2024
Conduct final event walkthrough with vendors and staff | Facility Manager | 03/15/2024 | 03/18/2024 | Pending | Yes
Launch promotional campaign across social media channels | Marketing Manager | 03/01/2024 | 03/14/2024 | In Progress | No
Finalize logistics and on-site setup schedule | Logistics Lead | 03/10/2024 | 03/17/2024 | Pending | No
April 2024
Host the main event day operations | Event Lead | 04/15/2024 | 04/15/2024 | Pending | Yes
Conduct post-event feedback survey and analysis | Project Manager | 04/16/2024 | 04/25/2024 | Pending | No
Submit final budget report and project closure documentation | Finance Lead | 04/20/2024 | 04/30/2024 | Pending | Yes