## Event Planning Project Plan
Event Planning Project Plan
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
EVT-001 | Define Event Objectives and Scope | Project Manager | 2024-04-01 | 2024-04-05 | In Progress | $500.00
EVT-002 | Finalize Event Theme and Concept | Marketing Lead | 2024-04-06 | 2024-04-15 | To Do | $750.00
EVT-003 | Secure Venue and Permits | Logistics Coordinator | 2024-04-16 | 2024-04-30 | To Do | $5,000.00
EVT-004 | Develop Event Schedule and Agenda | Event Planner | 2024-05-01 | 2024-05-15 | To Do | $800.00
EVT-005 | Invitations and RSVP Management | Marketing Assistant | 2024-05-16 | 2024-06-15 | To Do | $300.00
EVT-006 | Arrange Catering and Beverages | Vendor Coordinator | 2024-05-17 | 2024-06-15 | To Do | $3,500.00
EVT-007 | Book Entertainment and Speakers | Program Director | 2024-05-18 | 2024-06-15 | To Do | $4,750.00
EVT-008 | Develop and Distribute Promotional Materials | Marketing Team | 2024-05-20 | 2024-06-15 | To Do | $1,800.00
EVT-009 | Finalize Event Logistics and Run Sheet | Event Manager | 2024-06-16 | 2024-07-15 | To Do | $950.00
EVT-010 | Event Day Execution and Coordination | Project Manager & Team | 2024-07-16 | 2024-07-16 | To Do | $5,000.00
EVT-011 | Post-Event Evaluation and Reporting | Project Manager | 2024-07-17 | 2024-07-31 | To Do | $650.00
Total Project Budget: | [5 empty] | $23,700.00