## Worksheet
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | % Complete
EVT-001 | Define Event Objectives and Scope | Project Manager | 2023-10-01 | 2023-10-05 | In Progress | 75%
EVT-002 | Select Event Date and Venue | Event Coordinator | 2023-10-06 | 2023-10-15 | In Progress | 50%
EVT-003 | Develop Event Budget and Approve Funding | Finance Lead | 2023-10-16 | 2023-10-25 | To Do | 0%
EVT-004 | Finalize Guest List and Send Invitations | Marketing Team | 2023-10-18 | 2023-11-05 | To Do | 0%
Milestone: Event Planning Phase Complete (Nov 5, 2023)
EVT-005 | Book Catering and Entertainment | Logistics Manager | 2023-11-06 | 2023-11-15 | To Do | 0%
EVT-006 | Design and Distribute Event Materials (Banners, Programs) | Graphic Designer | 2023-11-08 | 2023-11-25 | To Do | 0%
EVT-007 | Coordinate Vendor Deliveries and Setup Schedule | Operations Lead | 2023-11-20 | 2023-11-30 | To Do | 0%
EVT-008 | Conduct Final Site Walkthrough and Risk Assessment | Project Manager | 2023-11-28 | 2023-11-30 | To Do | 0%
Milestone: Event Execution Phase Complete (Nov 30, 2023)
EVT-009 | Conduct Post-Event Evaluation and Feedback Collection | Project Manager | 2023-12-01 | 2023-12-15 | To Do | 0%
EVT-010 | Compile Final Budget Report and Financial Review | Finance Lead | 2023-12-16 | 2023-12-31 | To Do | 0%
EVT-011 | Send Thank You Notes and Share Event Recap | Marketing Team | 2023-12-31 | 2024-01-05 | To Do | 0%
Milestone: Project Closure and Final Report Submission (Jan 5, 2024)