## Worksheet
Event Planning Project Plan
Task ID | Task Description | Responsible Team Member | Start Date | End Date | Status | Budget Allocated ($)
EP-001 | Define Event Objectives and Scope | Project Manager | 2023-10-05 | 2023-10-15 | In Progress | 5,000.00
EP-002 | Select Event Venue and Confirm Booking | Logistics Coordinator | 2023-10-16 | 2023-11-05 | Pending | 8,500.00
EP-003 | Develop Event Marketing Strategy and Materials | Marketing Manager | 2023-11-06 | 2023-11-30 | Pending | 6,750.00
EP-004 | Coordinate Catering and Food Services | Catering Lead | 2023-11-15 | 2023-12-15 | Pending | 4,800.00
EP-005 | Book Entertainment and Keynote Speakers | Talent Coordinator | 2023-11-20 | 2023-12-10 | Pending | 7,950.00
EP-006 | Create Event Schedule and Timeline (Final) | Event Planner | 2023-12-15 | 2023-12-25 | Pending | 4,500.00
EP-007 | Send Invitations and Track RSVPs | Marketing Assistant | 2023-12-26 | 2024-01-15 | Pending | 3,750.00
EP-008 | Final Event Setup and Site Inspection | Operations Manager | 2024-01-16 | 2024-01-31 | Pending | 9,850.00
EP-009 | Event Day Execution and Onsite Management | Project Manager & Team | 2024-02-01 | 2024-02-01 | Pending | 6,550.00
EP-010 | Post-Event Evaluation and Reporting | Analyst | 2024-02-05 | 2024-02-15 | Pending | 3,450.00
Total Budget: | [5 empty] | $57,100.00