## Event Planning - Project Plan
Event Planning - Project Plan
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
EVT-001 | Define Event Objectives and Scope | Project Manager | 2024-03-01 | 2024-03-05 | In Progress | $500.00
EVT-002 | Select Event Venue | Logistics Coordinator | 2024-03-06 | 2024-03-15 | To Do | $3,500.00
EVT-003 | Develop Event Budget and Approval Process | Finance Lead | 2024-03-16 | 2024-03-25 | To Do | $1,800.00
EVT-004 | Secure Sponsorships and Partnerships | Sales & Partnerships Manager | 2024-03-18 | 2024-04-15 | To Do | $8,500.00
EVT-005 | Create Event Marketing and Promotion Strategy | Marketing Manager | 2024-03-26 | 2024-05-15 | To Do | $5,700.00
EVT-006 | Finalize Event Program and Speaker Schedule | Program Coordinator | 2024-04-16 | 2024-05-31 | To Do | $3,200.00
EVT-007 | Organize On-Site Logistics (Setup, AV, Catering) | Operations Lead | 2024-05-16 | 2024-06-15 | To Do | $18,900.00
EVT-008 | Conduct Final Event Walkthrough and Dry Run | Project Manager | 2024-06-16 | 2024-06-23 | To Do | $1,500.00
EVT-009 | Execute Event and Manage On-Site Operations | All Team Members | 2024-06-24 | 2024-06-25 | To Do | $15,300.00
EVT-010 | Post-Event Evaluation and Reporting | Project Manager & Analysts | 2024-06-26 | 2024-07-15 | To Do | $3,800.00
Total Estimated Budget:$62,700.00