## Worksheet
Quarterly Project Plan - Event Planning
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | Notes
Q1: January - March 2024
TASK-001 | Define event objectives and target audience | Project Manager | Jan 1, 2024 | Jan 15, 2024 | In Progress | Finalize KPIs and success metrics.
TASK-002 | Select event venue and book date | Logistics Coordinator | Jan 10, 2024 | Feb 5, 2024 | Not Started | Pending vendor availability.
Q2: April - June 2024
TASK-003 | Develop event program and speaker lineup | Content Lead | Apr 1, 2024 | May 15, 2024 | Not Started | Contact confirmed speakers.
TASK-004 | Create marketing and promotion campaign | Marketing Team | Apr 15, 2024 | Jun 1, 2024 | To Do | Schedule social media calendar.
Q3: July - September 2024
TASK-005 | Finalize event budget and secure sponsorships | Finance Manager | Jul 1, 2024 | Aug 15, 2024 | To Do | Leverage past event data.
Q4: October - December 2024
TASK-006 | Conduct full event rehearsal and dry run | Event Lead | Sep 30, 2024 | Oct 15, 2024 | To Do | Incorporate feedback from team.
TASK-007 | Post-event evaluation and report delivery | Project Manager | Dec 1, 2024 | Dec 15, 2024 | To Do | Analyze attendee feedback.