## Worksheet
Task ID | Task Name | Responsible Person(s) | Start Date | End Date | Status | Budget Allocated ($)
T001 | Define Event Objectives & Scope | Project Manager, Sponsor | 2023-10-05 | 2023-10-10 | In Progress | 5,000.00
T002 | Select Event Date & Venue | Logistics Coordinator, Venue Manager | 2023-10-11 | 2023-10-18 | Not Started | 8,500.00
T003 | Create Guest List & Send Invitations | Marketing Lead, Admin Assistant | 2023-10-19 | 2023-11-5 | In Progress | 4,750.00
T004 | Finalize Catering & Menu Selection | Catering Manager, Event Planner | 2023-11-6 | 2023-11-8 | Not Started | 7,900.00
T005 | Hire & Schedule Entertainment | Entertainment Coordinator, Vendor Manager | 2023-11-9 | 2023-11-15 | In Progress
T006 | Design & Print Event Materials (Banners, Programs) | Graphic Designer, Admin Assistant | 2023-11-6 | 2023-11-14 | In Progress | 3,400.00
T007 | Conduct Full Event Rehearsal & Dry Run | Project Manager, Team Leads | 2023-11-25 | 2023-11-30 | Pending Approval
T008 | Coordinate On-site Setup & Staff Assignments | Floor Manager, Operations Lead | 2023-12-052023-12-14In Progress6,800.00
T009 | Event Day Execution & Management | All Team Leads, Volunteers
T010 | Post-Event Evaluation & Report Compilation | Project Manager, Data Analyst2023-12-15 | 2023-12-31 | Pending Approval | 4,500.00
Total Project Budget:$59,750.00
Estimated Completion Date:December 31, 2023
Note: This is a report version of the project plan for internal review and tracking purposes.