## Event Planning - Project Plan
Task ID | Task Name | Assigned To | Start Date | End Date | Status
TASK001 | Define Event Goals & Objectives | Project Manager | 2024-01-05 | 2024-01-10 | To Do
TASK002 | Select Venue & Confirm Booking | Event Coordinator | 2024-01-11 | 2024-01-18 | In Progress
TASK003 | Develop Event Timeline & Schedule | Event Planner | 2024-01-15 | 2024-01-25 | In Progress
TASK004 | Finalize Guest List & Send Invitations | Marketing Team | 2024-01-18 | 2024-01-31 | To Do
TASK005 | Arrange Catering & Menu Approval | Catering Manager | 2024-01-20 | 2024-01-31 | In Progress
TASK006 | Confirm Audiovisual & Technical Setup | Technical Lead | 2024-01-25 | 2024-01-31 | To Do
TASK007 | Coordinate with Speakers & Performers | Event Coordinator | 2024-01-28 | 2024-02-15 | To Do
TASK008 | Conduct Final Event Walkthrough | Project Manager | 2024-02-16 | 2024-02-17 | To Do
TASK009 | Event Execution & On-Site Management | All Team Members | 2024-02-18 | 2024-02-18 | To Do
TASK010 | Post-Event Evaluation & Reporting | Project Manager | 2024-02-19 | 2024-03-01 | To Do