## Event Planning - Project Plan
Event Planning - Project Plan
Task ID | Task Name | Responsible Person | Start Date | End Date | Status
T001 | Define Event Objectives | Jane Doe | 2024-11-05 | 2024-11-08 | In Progress
T002 | Select Venue & Date | John Smith | 2024-11-09 | 2024-11-15 | Pending
T003 | Create Guest List & Invitations | Sarah Lee | 2024-11-16 | 2024-11-25 | Pending
T004 | Secure Catering & Refreshments | Mike Johnson | 2024-11-18 | 2024-11-30 | Pending
T005 | Book Entertainment & Speakers | Lisa Brown | 2024-11-20 | 2024-12-03 | Pending
T006 | Develop Event Schedule & Agenda | Jane Doe | 2024-11-25 | 2024-11-30 | Pending
T007 | Set Up Registration & RSVP System | John Smith | 2024-11-26 | 2024-12-05 | Pending
T008 | Finalize Budget & Approvals | Mary Wilson | 2024-11-30 | 2024-12-06 | Pending
T009 | Distribute Event Materials & Communications | Sarah Lee | 2024-12-05 | 2024-12-10 | Pending
T010 | Event Day Coordination & On-site Setup | All Team Members | 2024-12-15 | 2024-12-15 | Pending
Total Tasks: 10 ¦ Completed: 0 ¦ In Progress: 1 ¦ Pending: 9