## Worksheet
Event Planning - Startup Project Plan
Project Timeline & Task Management Dashboard
Task ID | Task Description | Owner | Due Date | Status | Priority
EVT-001 | Define event vision and objectives | Alice Chen | 2024-04-15 | Pending | High
EVT-002 | Select event venue and confirm booking | Mark Wilson | 2024-04-18 | In Progress | High
EVT-003 | Develop event marketing strategy & materials | Sophia Lee | 2024-04-25 | In Progress | Medium
EVT-004 | Finalize event program & speaker confirmations | James Reed | 2024-05-01 | Pending | High
EVT-005 | Setup event registration and ticketing system | Lisa Patel | 2024-04-28 | Completed | Medium
EVT-006 | Coordinate logistics: AV, catering, signage | Daniel Kim | 2024-05-10 | In Progress | High
EVT-007 | Conduct final walkthrough and dry run | Alice Chen | 2024-05-15 | Pending | High
EVT-008 | Post-event evaluation & feedback collection | Sophia Lee | 2024-05-16 | Pending | Low
© 2024 Startup Event Planning Dashboard • Project Plan Template