## Worksheet
Task ID | Task Name | Start Date | End Date | Status | Responsible Team Member | Budget (USD)
EVT-001 | Define Event Objectives & Scope | 2023-10-01 | 2023-10-05 | In Progress | Sarah Johnson | $5,000
EVT-002 | Develop Event Theme & Concept | 2023-10-06 | 2023-10-15 | Not Started | Marcus Lee | $8,500
EVT-003 | Secure Event Venue & Permits | 2023-10-16 | 2023-10-31 | Not Started | Lisa Chen | $45,000
EVT-004 | Arrange Catering & Vendor Contracts | 2023-11-01 | 2023-11-30 | Not Started | Jamal Williams | $65,000
EVT-005 | Create Marketing Materials & Campaign Plan | 2023-11-15 | 2023-12-15 | Not Started | Aisha Patel | $30,000
EVT-006 | Finalize Guest List & Invitations | 2023-12-16 | 2023-12-31 | Not Started | Sarah Johnson | $7,500
EVT-007 | Event Day Coordination & Setup | 2024-01-15 | 2024-01-15 | Not Started | All Team Members | $35,000
Total Budget: | [5 empty] | $241,000