## Worksheet
Event Planning Project Plan - Team Use
Task ID | Task Description | Responsible Team Member(s) | Start Date | End Date | Status | Budget Allocated ($)
EP-001 | Define Event Objectives & Scope | Project Lead, Marketing Team | 2024-05-01 | 2024-05-15 | To Do | 1,500.00
EP-002 | Select Venue & Secure Booking | Logistics Team, Facilities Manager | 2024-05-16 | 2024-05-31 | In Progress | 8,000.00
EP-003 | Develop Event Marketing Plan | Marketing Team, Graphic Designer | 2024-05-18 | 2024-06-15 | In Progress | 3,500.00
EP-004 | Finalize Guest List & Send Invitations | Events Coordinator, Admin Staff | 2024-06-16 | 2024-07-15 | To Do | 500
EP-005 | Arrange Catering & Dietary Options | Catering Team, Procurement Lead | 2024-06-18 | 2024-07-15 | In Progress | 6,500.00
EP-006 | Coordinate Audiovisual & Stage Setup | Technical Team, AV Specialist | 2024-07-15 | 2024-07-31 | To Do | 4,800.00
EP-007 | Conduct Final Event Rehearsal | All Teams, Project Lead | 2024-08-15 | 2024-08-17 | To Do | 1,200.00
EP-008 | Execute Event Day Operations | All Team Members | 2024-08-18 | 2024-08-19 | To Do | 7,500.00
EP-009 | Post-Event Survey & Feedback Collection | Project Lead, HR Team | 2024-08-20 | 2024-08-31 | To Do | 600
EP-999 | Closing Report & Lessons Learned Session | Project Lead, Team Leads | 2024-09-01 | 2024-09-15 | To Do | 800
Total Budget Allocated:$41,400.00
Completed Tasks:2 / 10
Status Update Date:April 5, 2024