## Worksheet
Event Planning Project Plan Template
Task ID | Task Description | Responsible Person | Start Date | End Date | Status
TP-001 | Define Event Objectives & Goals | Project Manager | 2024-01-05 | 2024-01-10 | To Do
TP-002 | Select Event Date & Venue | Event Coordinator | 2024-01-11 | 2024-01-18 | In Progress
TP-003 | Create Guest List & Send Invitations | Marketing Assistant | 2024-01-19 | 2024-01-31 | In Progress
TP-004 | Finalize Event Program & Schedule | Program Director | 2024-01-25 | 2024-01-31 | To Do
TP-005 | Arrange Catering & Food Service | Catering Manager | 2024-01-15 | 2024-01-31 | In Progress
TP-006 | Book Entertainment & Speakers | Entertainment Lead | 2024-01-18 | 2024-01-31 | In Progress
TP-007 | Set Up Event Signage & Branding | Design Team | 2024-01-28 | 2024-01-31 | To Do
TP-008 | Conduct Final Event Rehearsal | Project Manager | 2024-01-30 | 2024-01-31 | To Do
TP-009 | Execute Event Day Operations | All Team Members | 2024-02-01 | 2024-02-01 | Not Started
TP-010 | Post-Event Survey & Evaluation | Data Analyst | 2024-02-03 | 2024-02-15 | Not Started
Total Tasks: |  |  |  |  | 10