## Worksheet
Task ID | Task Description | Owner | Start Date | End Date | Status | % Complete
Phase 1: Event Planning & Preparation
PLN-001 | Define event objectives and goals | Jane Smith | 2024-01-15 | 2024-01-25 | On Track | 95%
PLN-002 | Set event theme and concept | Mark Johnson | 2024-01-18 | 2024-01-31 | On Track | 90%
Phase 2: Logistics & Vendor Management
LOG-001 | Book venue and confirm availability | Sarah Lee | 2024-01-20 | 2024-02-15 | On Track | 85%
LOG-002 | Hire catering and food service provider | Raj Patel | 2024-01-25 | 2024-03-15 | On Track | 75%
Phase 3: Marketing & Promotion
MRK-001 | Create event website and registration portal | Linda Chen | 2024-02-01 | 2024-03-15 | On Track | 88%
MRK-002 | Launch social media campaign and email outreach | Alex Turner | 2024-03-01 | 2024-05-15 | On Track | 67%
Phase 4: Final Preparations & Execution
FNL-001 | Finalize event schedule and program | Jane Smith | 2024-05-15 | 2024-06-15 | Delayed | 45%
Event Day: June 20, 2024 (Final Execution)