## Worksheet
Weekly Project Plan - Event Planning
Week Commencing | Task/Activity | Responsible Person | Status | Start Date | End Date | Budget Allocated ($) | Budget Spent ($) | Notes
Week 1: Planning & Setup
2023-04-03 | Define event objectives and scope | Jane Smith | To Do | 2023-04-03 | 2023-04-05 | $1,500.00 | $875.65 | Initial planning workshop scheduled.
2023-04-03 | Select venue and book date | Mark Johnson | In Progress | 2023-04-04 | 2023-04-15 | $8,500.00 | $6,789.56 | Venue contract signed.
Week 2: Vendor & Guest Management
2023-04-10 | Finalize vendor contracts (catering, AV) | Lisa Chen | In Progress | 2023-04-11 | 2023-04-17 | $5,800.00 | $4,956.78 | Catering proposal approved.
2023-04-11 | Send out guest invitations (digital & print) | Tony Reed | To Do | 2023-04-15 | 2023-04-19 | $750.89 | Printing due April 17.
Week 3: Logistics & Rehearsals
2023-04-17 | Organize transportation and accommodation for speakers | Alice Brown | To Do | 2023-04-18 | 2023-04-25 | $3,950.45 | Booking confirmed for 6 guests.
2023-04-18 | Conduct full event rehearsal | David Kim | In Progress | 2023-04-19 | 2023-04-19 | $50.78 | Rehearsal successful; minor adjustments needed.
Week 4: Final Preparations & Execution
2023-04-24 | Finalize event schedule and speaker assignments | Jane Smith | In Progress | 2023-04-19 | 2023-04-26 | $1,855.67 | Schedule finalized and distributed.
2023-04-25 | Site setup and final checks (decor, equipment) | Mark Johnson | To Do | 2023-04-18 | 2023-04-30 | $6,589.76 | Event day setup scheduled.
Total Budget: | [5 empty] | $28,000.55 | $29,436.74 | Over budget by $1,436.19 (Review needed).
This plan is updated weekly. Last updated: April 25, 2023.