## Worksheet
Event Planning - Advanced Project Template
Task ID | Task Name | Description | Owner | Due Date | Priority | Status | Progress (Completion)
Planning & Strategy
PLN-001 | Define Event Objective | Determine purpose, target audience, and success metrics. | Project Manager | 2025-04-15 | High | Status: In Progress
PLN-002 | Set Budget Allocation | Create detailed budget with contingencies and cost centers. | Finance Lead | 2025-04-18 | High | Status: Not Started
Venue & Logistics
VEN-001 | Secure Event Venue | Select and contract a venue matching capacity and location needs. | Logistics Coordinator | 2025-04-25 | High | Status: In Progress
VEN-002 | Arrange Permits & Insurance | Obtain necessary local permits and event liability insurance. | Legal & Compliance Officer | 2025-04-30 | Medium | Status: Not Started
Marketing & Communications
MKT-001 | Design Branding & Assets | Create logo, theme, banners, and digital graphics. | Marketing Designer | 2025-04-20 | High | Status: In Progress
MKT-002 | Launch Social Media Campaign | Post teasers, countdowns, and interactive content across platforms. | Social Media Manager | 2025-05-10 | Medium | Status: Not Started
Attendees & Registrations
REG-001 | Set Up Registration Portal | Configure online registration system with payment integration. | IT Specialist | 2025-04-12 | High | Status: Completed
REG-002 | Send Invitations & Reminders | Distribute invites via email and track RSVPs. | Email Coordinator | 2025-04-30 | Medium | Status: Not Started
On-Site Operations
OPS-001 | Develop Event Schedule & Agenda | Create detailed timeline with speaker sessions, breaks, and activities. | Event Planner | 2025-05-05 | High | Status: In Progress
OPS-002 | Coordinate Vendor Setup | Confirm arrival times, equipment delivery, and setup requirements. | Venue Manager | 2025-05-18 | Medium | Status: Not Started
Post-Event
PST-001 | Send Post-Event Survey | Gather feedback from attendees and stakeholders. | Project Coordinator | 2025-05-25 | Low | Status: Not Started
PST-002 | Compile Final Report & ROI Analysis | Analyze KPIs, budget vs. actuals, and success outcomes. | Project Manager | 2025-06-15 | High | Status: Not Started
Event Planning Project Template – Advanced Version ¦ Last Updated: April 5, 2025