## Worksheet
Event Planning - Project Template - Analysis View
Task ID | Task Name | Responsible Team | Status | Start Date | End Date | Budget (USD)
EP-001 | Define Event Objectives | Planning Committee | In Progress | 2024-01-15 | 2024-01-25 | 5,000.00
EP-002 | Select Venue & Confirm Booking | Logistics Team | Not Started | 2024-01-26 | 2024-01-31 | 35,000.00
EP-003 | Develop Event Program & Schedule | Content Team | In Progress | 2024-01-18 | 2024-01-31 | 8,500.00
EP-004 | Create Marketing & Promotion Plan | Marketing Team | In Progress | 2024-01-15 | 2024-03-15 | 25,000.00
EP-005 | Secure Sponsorships & Partnerships | Sponsorship Team | Not Started | 2024-01-28 | 2024-03-15 | 75,000.00
EP-006 | Develop Attendee Registration System | Tech Team | In Progress | 2024-01-25 | 2024-03-15 | 15,000.00
EP-007 | Catering & Dining Arrangements | Logistics Team | Not Started | 2024-01-31 | 2024-03-15 | 45,000.00
EP-017 | Final Event Rehearsal & Dry Run | Planning Committee & Tech Team | Pending | 2024-04-15 | 2024-04-16 | 3,500.00
EP-999 | Total Estimated Budget Overview | Aggregate Summary | TOTAL: |  |  | $212,000.00