## Worksheet
Phase | Task Name | Responsible Party | Start Date | End Date | Status
Planning & Research | Define Event Objectives and Scope | Project Manager | 01-Jan-2024 | 15-Jan-2024 | In Progress
| Conduct Market & Audience Research | Marketing Team | 16-Jan-2024 | 31-Jan-2024 | Pending
| Create Initial Budget Proposal | Finance Coordinator | 01-Feb-2024 | 15-Feb-2024 | Pending
Logistics & Coordination | Select Venue and Confirm Booking | Operations Lead | 01-Mar-2024 | 15-Mar-2024 | Pending
| Arrange Vendor Contracts (Catering, AV, Decor) | Venue Coordinator | 16-Mar-2024 | 31-Mar-2024 | Pending
| Develop Event Schedule and Agenda | Event Planner | 01-Apr-2024 | 15-Apr-2024 | Pending
| Coordinate Staff and Volunteer Assignments | Hiring Manager | 16-Apr-2024 | 30-Apr-2024 | Pending
Promotion & Communication | Create Marketing Materials and Branding Assets | Design Team | 01-May-2024 | 15-May-2024 | Pending
| Launch Digital Campaign (Email, Social Media) | Marketing Specialist | 16-May-2024 | 31-May-2024 | Pending
| Send Invitations and Confirm RSVPs | Communication Officer | 01-Jun-2024 | 15-Jun-2024 | Pending
Execution & On-site Management | Final Site Walkthrough and Setup Check | Event Manager | 01-Jul-2024 | 05-Jul-2024 | Pending
| On-site Staff Briefing and Run-through | Hospitality Lead | 06-Jul-2024 | 07-Jul-2024 | Pending
| Event Day Management and Real-time Adjustments | Project Manager | 08-Jul-2024 | 08-Jul-2024 | Pending
Post-Event Activities | Collect Feedback from Attendees and Stakeholders | Research Analyst | 09-Jul-2024 | 15-Jul-2024 | Pending
| Finalize Budget and Financial Reporting | Finance Manager | 16-Jul-2024 | 31-Jul-2024 | Pending
| Prepare Post-Event Summary and Lessons Learned Report | Project Manager | 01-Aug-2024 | 15-Aug-2024 | Pending
Annual Event Planning Summary - Key Metrics & Success Indicators
Total Budget Allocated: |  | $500,000
Target Attendance: |  | 1,500 attendees
Satisfaction Rate Goal: |  | 95%
Notes & Additional Information
This annual event planning template is designed for comprehensive project oversight. All tasks are aligned with a 12-month timeline. Status updates should be reviewed weekly. Adjustments may be made based on stakeholder feedback and budget variance.