## Event Planning Project Template
Event Planning Project Template
Task ID | Task Description | Responsible Person | Start Date | Due Date | Status
EVT-001 | Define event purpose and objectives | Project Manager | 2023-10-01 | 2023-10-05 | To Do
EVT-002 | Identify target audience and guest list | Marketing Lead | 2023-10-06 | 2023-10-10 | In Progress
EVT-003 | Select event date and venue | Event Coordinator | 2023-10-11 | 2023-10-15 | In Progress
EVT-004 | Develop event budget and secure funding | Finance Manager | 2023-10-16 | 2023-10-25 | To Do
EVT-005 | Create event program and schedule | Program Director | 2023-10-26 | 2023-11-05 | To Do
EVT-006 | Design and send invitations | Marketing Lead | 2023-11-06 | 2023-11-15 | To Do
EVT-007 | Arrange catering and refreshments | Catering Manager | 2023-11-16 | 2023-11-25 | To Do
EVT-008 | Coordinate audiovisual and technical setup | Technical Lead | 2023-11-26 | 2023-12-05 | To Do
EVT-009 | Confirm vendor contracts and payments | Procurement Officer | 2023-12-06 | 2023-12-15 | To Do
EVT-010 | Conduct event rehearsal and walkthrough | Event Coordinator | 2023-12-16 | 2023-12-18 | To Do
EVT-011 | Execute event day operations | All Team Members | 2023-12-19 | 2023-12-19 | To Do
EVT-012 | Collect feedback and evaluate success metrics | Project Manager | 2023-12-20 | 2023-12-31 | To Do
This template is designed for basic event planning projects with clear milestones and responsibilities.