## Event Planning - Client View
Event Planning - Client View
Task ID | Task Description | Assigned To | Status | Due Date | Budget Allocation ($)
EVT-001 | Finalize Event Concept & Theme | Marketing Team | Completed | 2023-10-15 | 1,500.00
EVT-002 | Select Venue & Confirm Booking | Logistics Coordinator | In Progress | 2023-11-05 | 8,500.00
EVT-003 | Coordinate Catering & Menu Approval | Catering Manager | Pending Review | 2023-11-10 | 6,250.00
EVT-004 | Design & Distribute Invitations | Graphic Designer | Pending Review | 2023-11-08 | 950
EVT-005 | Book Entertainment & Performers | Talent Coordinator | Pending Confirmation | 2023-11-15 | 4,800.00
EVT-006 | Finalize Guest List & RSVP Tracking | Event Manager | In Progress | 2023-11-25 | 400
EVT-007 | Organize On-Site Setup & Decorations | Decor Team Lead | Pending Review | 2023-12-01 | 5,600.00
EVT-008 | Conduct Final Event Walkthrough | Project Director | Scheduled | 2023-12-05 | 750