## Worksheet
Task ID | Task Name | Start Date | End Date | Assigned To | Status | Priority | Budget (USD)
EP001 | Define Event Objective | 2023-10-01 | 2023-10-05 | Jane Smith | To Do | High | $5,000.00
EP002 | Select Venue & Confirm Availability | 2023-10-15 | 2023-10-19 | Mike Johnson | In Progress | High | $45,000.00
EP003 | Develop Event Program & Agenda | 2023-11-15 | 2023-11-17 | Sarah Lee | To Do | Medium | $8,000.00
EP004 | Secure Speakers & Presenters | 2023-11-18 | 2023-11-30 | Lisa Wang | In Progress | High | $35,000.00
EP005 | Create Marketing & Promotion Plan | 2023-11-15 | 2023-11-30 | David Brown | In Progress | Medium | $7,500.00
EP006 | Manage Registration & Ticketing System | 2023-11-15 | 2023-12-31 | Amy Garcia | To Do | High | $6,000.00
EP007 | Organize Catering & Hospitality Services | 2023-11-15 | 2024-01-31 | James Wilson | To Do | High | $50,000.00
EP008 | Coordinate Logistics & Vendor Setup | 2023-12-15 | 2024-01-31 | Tina Patel | To Do | High | $38,000.00
EP009 | Conduct Event Rehearsal & Dry Run | 2024-01-31 | 2024-01-31 | All Team Members | To Do | High | $5,500.00
EP010 | Capture Event Feedback & Post-Event Report | 2024-03-15 | 2024-03-31 | Jane Smith | To Do | Medium | $3,500.00
Total Estimated Budget: | [6 empty] | $258,500.00