## Event Planning - Employee View
Event Planning - Employee View
Task ID | Task Description | Assigned To | Due Date | Status | Prioritization Level | Progress (%)
EVT-001 | Finalize event venue contract | Jane Smith | 2023-10-15 | In Progress | High | 75%
EVT-002 | Create guest list and send invitations | Mark Johnson | 2023-10-18 | Pending | Medium | 25%
EVT-003 | Confirm catering menu and final order | Sarah Lee | 2023-10-16 | In Progress | High | 60%
EVT-004 | Arrange audiovisual equipment setup | David Chen | 2023-10-17 | Pending | Medium | 10%
EVT-005 | Develop event program and schedule | Lisa Parker | 2023-10-14 | Completed | High | 100%
EVT-006 | Coordinate with keynote speaker | Tony Williams | 2023-10-19 | Pending | High | 5%
EVT-007 | Prepare event signage and materials | Amy Rodriguez | 2023-10-15 | In Progress | Low | 45%
EVT-008 | Conduct final walkthrough and site check | Raj Patel | 2023-10-20 | Pending | High | 0%
EVT-009 | Collect feedback forms after event | Sophia Brown | 2023-10-25 | Pending | Medium | 0%
EVT-010 | Finalize budget reconciliation report | Linda Garcia | 2023-11-05 | Pending | Medium | 0%
This table is an interactive project template for event planning. Status indicators and progress percentages can be updated in real-time.