## Event Planning - Financial View
Event Planning - Financial View
Category | Item Description | Budgeted (USD) | Actual (USD) | Variance (USD) | % of Budget | Status | Notes
Event Expenses
1 | Venue Rental | $15,000.00 | $14,500.00 | $-500.00 | 96.7% | In Budget | Early booking discount applied.
2 | Catering (Per Person) | $4,500.00 | $4,750.00 | $250.00 | 113.6% | Over Budget | Slight increase in guest count.
3 | AV Equipment & Technician | $3,200.00 | $3,150.00 | $-50.00 | 98.4% | In Budget | Used existing equipment.
4 | Decor, Signage, and Branding | $2,800.00 | $2,950.00 | $150.00 | 114.3% | Over Budget | Additional custom designs requested.
5 | Digital Advertising & Event Promotion | $3,500.00 | $3,250.00 | $-250.00 | 92.9% | In Budget | Optimized ad spend.
6 | Event Staff & Volunteers | $2,400.00 | $2,350.00 | $-50.00 | 97.9% | In Budget | Volunteers covered part of the team.
7 | Contingency Fund (10%) | $3,545.00 | $2,895.00 | $-650.00 | 81.7% | In Budget | Unused portion retained.
Total Event Expenses |  | $35,445.00 | $32,895.00 | $-2,550.00 | 91.7% | Under Budget
Additional Revenue Sources
1 | Sponsorship Contributions | $5,000.00 | $5,250.00 | $250.00 | 113.6% | Over Budget | Extra sponsor added last minute.
2 | Ticket Revenue (Online) | $18,000.00 | $17,850.00 | $-150.00 | 99.2% | In Budget | Minor drop in registration.
Total Additional Revenue |  | $23,000.00 | $23,100.00 | $150.05 | 114.3% | Over Budget
Net Financial Summary
Total Revenue - Total Expenses |  | $23,000.00 | $23,100.00 | $1545.95 | 167.8% | Profit Margin Achieved