## Worksheet
Event Planning Project Template
Freelancer Style ¦ Purpose: Event Planning ¦ Template Type: Project Template
Task ID | Task Description | Category | Assigned To | Status | Due Date | Budget (USD)
Planning & Strategy
PLN-001 | Define event objective and target audience | Strategy | [Assign] | Pending | 2024-12-05 | $0.00
PLN-002 | Select event theme and concept | Concept Development | [Assign] | Pending | 2024-12-10 | $50.00
Venue & Logistics
VEN-001 | Research and shortlist potential venues | Logistics | [Assign] | In Progress | 2024-12-15 | $300.00
VEN-002 | Negotiate venue contract and deposit payment | Contract Management | [Assign] | Pending | 2024-12-18 | $1,500.00
Vendor Coordination
VDR-001 | Book catering services (menu selection, tasting) | Catering | [Assign] | Pending | 2025-01-15 | $800.00
VDR-002 | Arrange audiovisual equipment and technical support | AV & Technology | [Assign] | Pending | 2025-01-10 | $650.00
Marketing & Communications
MKT-001 | Create event invitation (digital and print) | Design | [Assign] | Pending | 2025-01-25 | $250.00
MKT-002 | Launch social media campaign and email invitations | Marketing | [Assign] | Pending | 2025-01-30 | $400.00
Day-of Coordination
DAY-001 | Final walkthrough with venue and vendors | Event Management | [Assign] | Pending | 2025-02-14 | $300.00
DAY-002 | Coordinate event staff and volunteers on-site | Staffing | [Assign] | Pending | 2025-02-14 | $500.00
Post-event Activities
POST-001 | Send thank-you notes to attendees and vendors | Closing | [Assign] | Pending | 2025-02-18 | $75.00
Total Estimated Budget: | [5 empty] | $5,325.00
Note:Replace [Assign] with team member names. Adjust dates and budget as needed based on project scope. This template is designed for freelancers managing small to mid-sized events.