## Worksheet
Event Planning Project Template
Large Business Style - Comprehensive Planning & Execution Framework
Phase | Task Name | Responsible Party | Start Date | End Date | Status | Budget (USD)
Planning & Strategy | Define Event Objectives & KPIs | Event Director | 2024-01-05 | 2024-01-15 | In Progress | $5,000.00
| Conduct Stakeholder Analysis | Project Manager | 2024-01-16 | 2024-01-31 | Pending | $3,500.00
| Develop Event Concept & Theme | Marketing Team Lead | 2024-01-18 | 2024-02-15 | Pending | $7,800.00
Logistics & Coordination | Secure Venue & Permits | Logistics Coordinator | 2024-02-01 | 2024-03-15 | Pending | $45,675.30
| Arrange Catering & Hospitality Services | Vendor Relations Manager | 2024-02-15 | 2024-04-15 | Pending | $38,999.75
| Coordinate AV & Technical Setup | IT & AV Lead | 2024-03-01 | 2024-05-15 | Pending | $31,456.89
| Plan Transportation & Accommodations | Travel Coordinator | 2024-03-10 | 2024-05-31 | Pending | $57,893.56
Marketing & Engagement | Design Branded Materials & Collateral | Design Team Lead | 2024-01-20 | 2024-03-31 | Pending | $18,755.98
| Launch Digital Campaigns (Email/Social) | Marketing Specialist | 2024-03-01 | 2024-06-15 | Pending | $45,678.33
| Develop Speaker & Guest Outreach Plan | Public Relations Manager | 2024-02-01 | 2024-05-31 | Pending | $17,987.65
| Organize Press & Media Coverage Strategy | Media Relations Lead | 2024-03-15 | 2024-06-30 | Pending | $15,789.41
Execution & On-Site Management | Finalize Event Schedule & Timeline | Event Project Manager | 2024-05-15 | 2024-06-15 | Pending | $8,976.33
| Conduct On-Site Rehearsal & Tech Check | Event Technical Director | 2024-06-15 | 2024-06-17 | Pending | $9,387.55
| On-Site Event Management & Coordination | Event Lead Team | 2024-06-18 | 2024-06-19 | Pending | $45,678.99
Post-Event & Reporting | Conduct Post-Event Debrief & Feedback Collection | Project Analyst | 2024-06-20 | 2024-07-15 | Pending | $16,897.45
| Compile Performance Reports & ROI Analysis | Finance & Analytics Team | 2024-07-16 | 2024-08-15 | Pending | $19,335.78
| Archive Event Files & Document Lessons Learned | Knowledge Manager | 2024-08-16 | 2024-08-31 | Pending | $5,789.34
Total Estimated Budget | [5 empty] | $450,789.41