## Event Planning - Manager View
Task ID | Task Name | Owner | Start Date | Due Date | Status | % Complete
Event Planning - Annual Conference 2024
M1 | Finalize Event Concept & Budget | Project Manager | 2024-01-15 | 2024-01-31 | In Progress | 75%
T1.1 | Create Event Proposal Document | Marketing Lead | 2024-01-15 | 2024-01-20 | Completed | 100%
T1.2 | Approve Budget with Finance Team | Finance Manager | 2024-01-21 | 2024-01-31 | In Progress | 60%
M2 | Secure Venue and Catering | Project Manager | 2024-02-15 | 2024-03-15 | To Do | 0%
T2.1 | Research and Shortlist 3 Venues | Operations Coordinator | 2024-02-15 | 2024-02-25 | To Do | 0%
T2.2 | Negotiate Contract with Preferred Venue | Project Manager | 2024-03-01 | 2024-03-15 | To Do | 0%
M3 | Launch Registration & Promotions | Marketing Team | 2024-04-15 | 2024-06-30 | To Do | 0%
T3.1 | Design Registration Website Page | UX Designer | 2024-04-15 | 2024-05-05 | To Do | 0%
Total Tasks: 6 ¦ Completed: 1 ¦ In Progress: 2 ¦ To Do: 3