## Worksheet
Event Planning Project Template
Overview & Objectives
Item | Description
Project Name: | Annual Corporate Conference 2024
Event Type: | Conference / Networking Event
Planned Date: | 2024-10-15
Location: | Grand Convention Center, Downtown
Attendee Count: | 500+
Objective: | Enhance team collaboration, share strategic goals, and celebrate annual achievements.
Key Milestones
Phase | Milestone | Target Date | Status
Planning Initiation | Finalize Event Scope & Budget Approval | 2024-05-31 | Pending
Creative Development | Design Branding & Theme Concepts | 2024-06-30 | In Progress
Vendor Procurement | Secure Catering, Venue, Audiovisual Suppliers | 2024-07-31 | To Do
Marketing & Registration | Launch Registration Portal & Promotional Campaigns | 2024-08-31 | To Do
Event Execution | Host the Event & Manage On-site Operations | 2024-10-15 | To Do
Closing Phase | Post-Event Survey & Final Report Submission | 2024-11-30 | To Do
Page 1 of 5 ¦ Event Planning Project Template ¦ Multi Page Version
Event Planning Project Template
Budget Breakdown
Category | Description | Estimated Cost (USD) | Actual Cost (USD)
Venue & Facilities | Rental, Setup, Breakdown | 25,000.00 | -
Catering Services | Meals & Refreshments (3 days) | 18,500.00 | -
Audiovisual Equipment | Projectors, Microphones, Lighting | 8,200.00 | -
Marketing & Promotion | Social media ads, email campaigns | 5,300.00 | -
Decor & Branding | Signage, Backdrops, Theme Elements | 6,800.00 | -
Staffing & Logistics | Event coordinators, security, transport | 12,400.00 | -
Contingency (10%) | Risk buffer for unforeseen costs | 8,355.00 | -
Total Estimated Cost: |  | 84,555.00 | -
Risk Assessment Matrix
Risk Factor | Description | Probability (1-5) | Impact (1-5) | Risk Score | Mitigation Strategy
Venue Cancellation | Fire, weather, or legal issues affecting venue access | 3 | 5 | 15 | Signed contract with backup venue; insurance policy applied.
Catering Failure | Food safety issue or late delivery | 2 | 4 | 8 | Select certified vendors with backup plans.
Low Attendance Rate | Lack of registrations or no-shows from key attendees | 4 | 3 | 12
Page 2 of 5 ¦ Event Planning Project Template ¦ Multi Page Version
Event Planning Project Template
Team Roles & Responsibilities
Role | Name (Optional) | Contact | Responsibilities
Project Manager | Jane Smith | jane.smith@company.com | Oversee entire project, manage timeline & budget, report to executive team.
Event Schedule (Sample Day)
Time | Activity | Location | Responsible Team
Page 3 of 5 ¦ Event Planning Project Template ¦ Multi Page Version
Event Planning Project Template
Vendor Information & Contracts
Vendor Name | Contact Person | Service Provided | Contract ID | Status (Signed/On Hold/Active)
Registration & Attendance Tracker (Sample)
Attendee ID | Name | Company | Email | Registration Date | Status (Confirmed/Waitlisted)
Page 4 of 5 ¦ Event Planning Project Template ¦ Multi Page Version
Event Planning Project Template
Post-Event Review & Feedback Summary
Feedback Area | Average Score (1–5) | Comments from Attendees
Final Report Summary
Key Success Metrics | Results