## Event Planning Project Template
Event Planning Project Template
Project Type: Event Planning ¦ Style/Version: Printable ¦ Date: _______________
Task ID | Task Description | Responsible Person | Start Date | Due Date | Status | Budget (USD)
EVT-001 | Define Event Objectives & Goals | Project Manager | 2023-10-01 | 2023-10-05 | In Progress | $50.00
EVT-002 | Select Venue & Confirm Booking | Logistics Coordinator | 2023-10-06 | 2023-10-15 | Not Started | $1,500.00
EVT-003 | Finalize Guest List & Send Invitations | Marketing Lead | 2023-10-16 | 2023-10-31 | Not Started | $75.00
EVT-004 | Arrange Catering & Menu Approval | Catering Manager | 2023-11-01 | 2023-11-10 | Not Started | $3,500.00
EVT-005 | Book Audiovisual & Technical Equipment | Technical Lead | 2023-11-11 | 2023-11-20 | Not Started | $900.00
EVT-006 | Create Event Schedule & Timeline | Project Manager | 2023-11-21 | 2023-11-30 | Not Started
EVT-007 | Coordinate Vendor Confirmations & Contracts | Procurement Officer | 2023-12-01 | 2023-12-15 | Not Started
EVT-008 | Final Walkthrough & Site Setup | Site Supervisor | 2023-12-16 | 2023-12-17
Total Budget: | [5 empty] | $5,975.00