## Worksheet
Event Planning Project Template (Report Version)
Project Name:Annual Tech Conference 2024
Project Manager:Sarah Thompson
Status:Planning Phase
Due Date:2024-10-15
Task ID | Task Description | Responsible Person | Start Date | End Date | Status | Budget (USD)
TASK001 | Finalize Event Concept & Theme | Sarah Thompson | 2024-03-01 | 2024-03-15 | In Progress | $1,500.00
TASK002 | Secure Venue & Confirm Capacity | Mark Johnson | 2024-03-16 | 2024-04-30 | In Progress | $8,500.00
TASK003 | Develop Speaker & Panelist List | Lisa Chen | 2024-04-15 | 2024-05-15 | In Progress | $3,750.00
TASK004 | Design Marketing & Promotion Plan | James Wilson | 2024-05-16 | 2024-07-31 | Pending Start | $5,600.00
TASK005 | Launch Ticket Sales Portal | Amy Patel | 2024-08-15 | 2024-10-15 | Pending Start | $3,800.00
TASK006 | Finalize Event Schedule & Logistics | Sarah Thompson | 2024-10-15 | 2024-11-30 | Pending Start | $6,950.00
TASK007 | Conduct Post-Event Review & Report | Mark Johnson | 2024-12-15 | 2025-01-31 | Pending Start | $4,800.00