## Worksheet
Task ID | Task Name | Assigned To | Start Date | End Date | Status
TASK001 | Define Event Objectives | John Doe | 2024-04-01 | 2024-04-03 | To Do
TASK002 | Select Venue | Jane Smith | 2024-04-04 | 2024-04-10 | In Progress
TASK003 | Finalize Guest List | Mike Brown | 2024-04-11 | 2024-04-15 | In Progress
TASK004 | Send Invitations | Sarah Wilson | 2024-04-16 | 2024-04-20 | To Do
TASK005 | Arrange Catering | David Lee | 2024-04-18 | 2024-04-25 | In Progress
TASK006 | Plan Event Schedule | Lisa Garcia | 2024-04-21 | 2024-04-30 | To Do
TASK007 | Coordinate Decorations & Layout | Chris Taylor | 2024-04-25 | 2024-05-01 | To Do
TASK008 | Conduct Final Rehearsal | Alex Martinez | 2024-05-02 | 2024-05-03 | To Do
TASK009 | Event Day Execution & Support | All Team Members | 2024-05-04 | 2024-05-04 | To Do
TASK010 | Post-Event Review & Feedback Collection | John Doe | 2024-05-05 | 2024-05-10 | To Do