## Worksheet
Event Planning - Startup Project Template
Track tasks, milestones, and resources for your next startup event
Task ID | Task Description | Assigned To | Due Date | Status | Budget (USD) | Actions
#EV-001 | Define event vision and objectives | Alice Johnson | 2024-06-15 | In Progress | $500.00 | EditUpdate Status
#EV-002 | Secure venue and negotiate contract | Bob Smith | 2024-06-18 | Pending | $3,500.00 | EditUpdate Status
#EV-003 | Finalize guest list and send invitations | Carol Davis | 2024-06-25 | Pending | $300.00 | EditUpdate Status
#EV-004 | Arrange catering and logistics | David Lee | 2024-07-15 | Pending | $4,200.00 | EditUpdate Status
#EV-005 | Coordinate speaker and panelist confirmations | Eva Brown | 2024-06-30 | In Progress | $1,200.00 | EditUpdate Status
#EV-006 | Develop event marketing campaign | Frank Wilson | 2024-07-10 | Pending | $3,800.00 | EditUpdate Status
#EV-007 | Set up registration and ticketing system | Gina Martinez | 2024-06-19 | Completed | $1,500.00 | EditUpdate Status
Total Budget: |  |  |  |  | $15,000.00