## Worksheet
Task | Owner | Due Date | Status | Priority | Progress (%)
Define Event Objectives | Jane Doe | 2024-05-10 | To Do | High | 0
Select Venue & Date | John Smith | 2024-05-15 | In Progress | High | 60
Create Guest List & Invitations | Sarah Lee | 2024-05-18 | In Progress | Medium | 40
Book Catering & Entertainment | Mike Johnson | 2024-05-20 | To Do | High | 0
Design Event Materials (Signage, Programs) | Lisa Wang | 2024-05-22 | To Do | Medium | 0
Finalize Event Schedule & Flow | Jane Doe | 2024-05-25 | To Do | High | 0
Total Tasks: |  |  |  |  | 100%