## Event Planning Project Timeline
Event Planning Project Timeline
Task ID | Task Description | Responsible Party | Start Date | End Date | Status | % Complete
EVT-001 | Define Event Objectives & Scope | Project Manager | 2023-10-05 | 2023-10-10 | Completed | 100%
EVT-002 | Secure Venue & Book Date | Logistics Coordinator | 2023-10-11 | 2023-10-25 | In Progress | 65%
EVT-003 | Develop Marketing Strategy | Marketing Lead | 2023-10-15 | 2023-11-05 | In Progress | 45%
EVT-004 | Finalize Guest List & Send Invitations | Event Coordinator | 2023-11-01 | 2023-11-15 | Pending | 0%
EVT-005 | Confirm Speakers & Presenters | Program Director | 2023-11-16 | 2023-11-30 | Pending | 0%
EVT-006 | Develop Event Agenda & Schedule | Program Coordinator | 2023-11-20 | 2023-11-30 | Pending | 5%
EVT-007 | Coordinate Catering & Refreshments | Catering Manager | 2023-11-25 | 2023-12-15 | Pending | 0%
EVT-008 | Arrange Audiovisual & Technical Setup | AV Technician | 2023-12-01 | 2023-12-15 | Pending | 0%
EVT-009 | Conduct Full Rehearsal Session | Event Director | 2023-12-18 | 2023-12-19 | Pending | 0%
EVT-010 | Execute Event Day Operations | All Team Members | 2023-12-20 | 2023-12-21 | Pending | 0%
EVT-011 | Post-Event Survey & Feedback Collection | Project Manager | 2023-12-22 | 2023-12-31 | Pending | 0%
EVT-012 | Final Report & Budget Review | Finance Lead | 2024-01-01 | 2024-01-15 | Pending | 0%
Note:This timeline is dynamically updated and reflects real-time project status. All dates are subject to change based on approvals and external dependencies.