## Worksheet
Task | Start Date | End Date | Status | Assigned To
Define Event Goals | 2024-01-01 | 2024-01-05 | Completed | Jane Doe
Select Venue | 2024-01-06 | 2024-01-15 | In Progress | John Smith
Create Guest List | 2024-01-16 | 2024-01-20 | Not Started | Alice Johnson
Send Invitations | 2024-01-21 | 2024-01-31 | Not Started | Alice Johnson
Confirm Catering Services | 2024-01-18 | 2024-01-25 | In Progress | Bob Brown
Arrange Audio/Visual Equipment | 2024-01-26 | 2024-01-31 | Not Started | Charlie Davis
Finalize Event Program | 2024-02-01 | 2024-02-05 | Not Started | Jane Doe
Event Day Coordination | 2024-02-10 | 2024-02-10 | Not Started | All Team Members