## Event Planning Project Timeline
Event Planning Project Timeline
Task ID | Task Description | Assigned To | Start Date | End Date | Status
EVT-001 | Define Event Objectives & Scope | Project Manager | 2024-04-01 | 2024-04-05 | In Progress
EVT-002 | Secure Venue & Book Date | Venue Coordinator | 2024-04-06 | 2024-04-15 | Pending Approval
EVT-003 | Create Event Budget & Approvals | Finance Lead | 2024-04-16 | 2024-04-25 | In Progress
EVT-004 | Develop Marketing & Promotion Plan | Marketing Specialist | 2024-04-18 | 2024-05-15 | In Progress
EVT-005 | Finalize Speaker & Guest List | Event Planner | 2024-04-28 | 2024-05-10 | Pending Review
EVT-006 | Coordinate Logistics & Vendor Contracts | Logistics Manager | 2024-05-01 | 2024-05-31 | To Do
EVT-007 | Conduct Final Event Walkthrough | Project Manager | 2024-06-15 | 2024-06-18 | To Do
EVT-008 | Execute Event Day Operations | All Team Members | 2024-06-19 | 2024-06-19 | To Do
EVT-009 | Post-Event Evaluation & Reporting | Project Manager | 2024-06-20 | 2024-06-30 | To Do
Legend:In Progress ¦ Pending Approval ¦ Pending Review ¦ To Do
This timeline is for business use and intended to support effective event planning.