## Worksheet
Event Planning Project Timeline - Client View
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Action Items
#001 | Finalize Event Concept & Theme | Marketing Team | 2024-04-05 | 2024-04-15 | Completed | View DetailsDownload Report
#002 | Secure Venue & Book Date | Event Coordinator | 2024-04-16 | 2024-04-30 | In Progress | View DetailsUpdate Status
#003 | Design & Distribute Invitations | Graphic Designer | 2024-05-01 | 2024-05-15 | Pending | View DetailsSet Reminder
#004 | Finalize Vendor Contracts (Catering, AV, etc.) | Procurement Manager | 2024-05-16 | 2024-05-31 | Pending | View DetailsSend Reminder
#005 | Conduct Team Briefing & Run-through | Project Lead | 2024-06-15 | 2024-06-17 | Pending | View DetailsSchedule Meeting
#006 | Event Day Execution & On-site Management | All Team Members | 2024-06-18 | 2024-06-18 | Pending | View DetailsChecklist
#007 | Post-Event Survey & Feedback Collection | Client Relations Officer | 2024-06-19 | 2024-06-25 | Pending | View DetailsSend Survey