## Worksheet
Task ID | Task Description | Assigned To | Start Date | End Date | Status | Budget (USD)
T001 | Define Event Goals & Objectives | Team Lead | 2024-04-05 | 2024-04-10 | Complete | $5,500
T002 | Secure Venue & Permits | Logistics Coordinator | 2024-04-11 | 2024-04-18 | In Progress | $35,000
T003 | Develop Marketing Strategy | Marketing Manager | 2024-04-12 | 2024-04-19 | In Progress | $18,750
T004 | Finalize Vendor Contracts | Procurement Lead | 2024-04-15 | 2024-04-25 | Pending | $67,890
T005 | Recruit & Train Staff | HR Manager | 2024-04-18 | 2024-04-30 | Pending | $15,675
T006 | Design Event Materials & Branding | Designer Team | 2024-04-19 | 2024-04-30 | Pending | $8,500
T007 | Conduct Final Site Inspection & Rehearsal | Event Director | 2024-05-15 | 2024-05-16 | Pending | $3,850
Project Summary
Tasks Completed
3 of 7On Track
3 of 7Delayed
1 of 7Total Budget